## Jobs 2026
Northside Home Repair - jobs 2026
updated 10/30, ask Mike before changing
Job # | Customer | Address | Work | Crew | Start | Due | Status | Quote | Paid? | Amount paid | Notes
J-1001 | Westside Fitness | 128 Hill Road | Repair window screens | Joe | 2026-07-29 | 2026-08-13 | On hold | 220
J-1002 | Oakwood Library | 169 Main Street | Fix leaking kitchen faucet | Joe | 2026-08-01 | 8/10/2026 | Done | 190 | Partial | $95.00
J-1003 | Bright Kids Learning Center | 243 Elm Street | Clean gutters | Joe | 2026-08-03 | 2026-08-09 | DONE | $205.00 | yes | 205
J-1004 | MAPLE STREET DENTAL | 195 Hill Road | Clean gutters | Chris | 8/5/2026 | 2026-08-13 | done | 270 | PAID | 270 | Customer supplies paint
J-1005 | Hillcrest Auto Care | 38 Cedar Court | Pressure wash patio | Ana | 2026-08-08 | 2026-08-23 | Done | 380 | No |  | Second visit needed
J-1006 | Maple Street Dental | 289 Birch Lane | Patch drywall in hallway | Mike | 2026-08-09 | 2026-08-16 | DONE | 315 | PAID | 315 | Parts on order
J-1007 | NINA PATEL | 99 Elm Street | Unit turnover repairs | joe | 2026-08-11 | Aug 15 | Done | 810 | Yes | $810.00 | Key with neighbor
J-1008 | green leaf cafe | 88 River Road | Install ceiling fan | Mike | 2026-08-13 | 2026-08-25 | Done | 365 | yes | 365 | Photos sent
J-1009 | Hillcrest Auto Care | 243 Orchard Way | Hang shelves in office | Joe | Aug 14 | 8/28/2026 | Done | $220.00 | Y | 220
J-1010 | Corner Print Shop | 58 Cedar Court | Repair window screens | Joe | 2026-08-17 | 2026-08-29 | Cancelled | 185 | N | 0 | Call before arriving
J-1011 | pinecrest realty | 215 Hill Road | Re-caulk bathtub | Mike | 8/19/2026 | 2026-08-27 | DONE | 160 | partial | 80
J-1012 | GREEN LEAF CAFE | 58 Park Avenue | Fix sticking doors | Mike | 2026-08-20 | 2026-09-01 | Done | 205 | part paid | $105.00
J-1013 | Lena Ortiz | 294 Birch Lane | Replace rotted deck boards | Chris | 2026-08-22 | 2026-09-02 | done | 1460 | PAID | 1460
J-1014 | Maple Street Dental | 102 Cedar Court | Fix sticking doors | Joe | 2026-08-25 | 2026-09-11 | Done | 180 | Y | 180
J-1015 | BRIGHT KIDS LEARNING CENTER | 121 Cedar Court | Re-caulk bathtub | mike | 2026-08-27 | 2026-09-14 | Done | $170.00 | No | 0 | Customer supplies paint
J-1016 | Hillcrest Auto Care | 60 Park Avenue | Fix sticking doors | Mike | 2026-08-28 | 9/12/2026 | done | 170 | Y | 170 | Second visit needed
J-1017 | nina patel | 52 Main Street | Re-caulk bathtub | Chris | 2026-08-29 | 2026-09-16 | Done | 145 | Partial | $75.00 | Parts on order
J-1018 | Pinecrest Realty | 225 Orchard Way | Install ceiling fan | Mike | 9/1/2026 | 2026-09-18 | Done | 310 | partial | 155 | Key with neighbor
J-1019 | HILLCREST AUTO CARE | 136 Park Avenue | Fix sticking doors | Mike | 2026-09-03 | 2026-09-18 | done | 235 | Yes | 235 | Photos sent
J-1020 | Westside Fitness | 290 Cedar Court | Fix leaking kitchen faucet | Joe | 2026-09-06 | Sep 25 | Done | 190 | yes | 190
J-1021 | Westside Fitness | 91 Birch Lane | Pressure wash patio | Joe | 2026-09-09 | 2026-09-12 | done | $355.00 | no |  | Call before arriving
J-1022 | Lena Ortiz | 122 Hill Road | Clean gutters | Mike | Sep 11 | 2026-09-14 | done | 240 | Partial | $120.00
J-1023 | Maple Street Dental | 27 Hill Road | Replace light fixtures | joe | 2026-09-14 | 9/17/2026 | Done | 480 | Y | 480
J-1024 | Bright Kids Learning Center | 112 River Road | Unit turnover repairs | Chris | 2026-09-17 | 2026-09-25 | Done | 865 | PAID | 865
J-1025 | Tom Becker | 180 Elm Street | Weatherstrip doors | Ana | 9/19/2026 | 2026-09-30 | Done | 195 | N
J-1026 | green leaf cafe | 269 Main Street | Pressure wash patio | Joe | 2026-09-22 | 2026-09-26 | Done | 300 | Yes | 300 | Customer supplies paint
J-1027 | SUNRISE BAKERY | 229 Orchard Way | Pressure wash patio | Joe | 2026-09-24 | 2026-10-10 | done | $360.00 | Yes | $360.00 | Second visit needed
J-1028 | MAPLE STREET DENTAL | 269 Elm Street | Re-caulk bathtub | Mike | 2026-09-26 | 2026-10-16 | cancelled | 175 | N | 0 | Parts on order
J-1029 | maple street dental | 160 Park Avenue | Repair fence section | Chris | 2026-09-28 | 2026-10-04 | done | 665 | Partial | 335 | Key with neighbor
J-1030 | Robert Chen | 290 Main Street | Install grab bars | Chris | 2026-09-30 | 10/20/2026 | Done | 240 | partial | 120 | Photos sent
J-1031 | ROBERT CHEN | 191 Cedar Court | Re-caulk bathtub | joe | 2026-10-02 | 2026-10-07 | In progress | 175 | no | 0
J-1032 | green leaf cafe | 110 Cedar Court | Assemble office furniture | Mike | 10/4/2026 | 2026-10-23 | DONE | 370 | Yes | $370.00 | Call before arriving
J-1033 | Hillcrest Auto Care | 29 Mill Street | Tile kitchen backsplash | Joe | 2026-10-06 | Oct 19 | Done | $920.00 | PAID | 920
J-1034 | Bright Kids Learning Center | 40 Main Street | Unit turnover repairs | Chris | 2026-10-08 | 2026-10-28 | In progress | 895 | No | 0
J-1035 | Sunrise Bakery | 162 Main Street | Unit turnover repairs | Ana | Oct 9 | 2026-10-17 | DONE | 825 | no | 0
J-1036 | maple street dental | 48 Main Street | Weatherstrip doors | Joe | 2026-10-11 | 2026-10-16 | Done | 255 | Yes | 255
J-1037 | ROBERT CHEN | 164 Mill Street | Clean gutters | Joe | 2026-10-14 | 10/25/2026 | done | 240 | Yes | $240.00 | Customer supplies paint
J-1038 | oakwood library | 45 Mill Street | Paint two bedrooms | Ana | 2026-10-16 | 2026-10-31 | DONE | 1740 | Partial | 870 | Second visit needed
J-1039 | hillcrest auto care | 205 Orchard Way | Install grab bars | chris | 10/18/2026 | 2026-11-03 | On hold | $265.00 | No | 0 | Parts on order
J-1040 | Harbor View Apartments | 265 Hill Road | Assemble office furniture | Chris | 2026-10-19 | 2026-11-07 | Scheduled | 485 | No | 0 | Key with neighbor
J-1041 | Corner Print Shop | 105 Orchard Way | Install ceiling fan | Ana | 2026-10-22 | 2026-10-30 | In progress | 285 | N |  | Photos sent
J-1042 | Sunrise Bakery | 13 Birch Lane | Repair window screens | Chris | 2026-10-25 | 2026-11-08 | Scheduled | 155 | No | 0
TOTAL | [7 empty] | 16870 |  | 10165